## Sheet1
Item | Importance | Comments | Status
Link from statpatient.com to production site | A | I will link from statpatient. What is production site link? | Done
Link from production site to statpatient.com | B | Link back to statpatient
Consent forms | B | Link back to statpatient
Patient Education | B | Link back to statpatient
Patient Profile | B | Link back to statpatient
Patient dropbox list doesn't align with box - font larger | A
Message Center Categories | A |  | Done
Inbox
Sent
Archive
Drafts |  | We didn't discuss drafts but show even if not functional
Drag and Drop | AA |  | Done but should have both options
Multiple Images | AA |  | Done
Align header box | A | Format issue
Change delete to archive - we need to retain all correspondance |  | Delete is ok if a draft but not if already sent
Manual sort of inbox - click sender, date, recipient, patient | B | Default sort date - newest first
Footer: Stat Patient, Inc. C 2014 All Rights Reserved | B
Case number - add default "optional" | B
Size subject same as Recipient and Patient box | C
Need Tooth chart(s) | AA |  | Need to have on original message
More color contrast "Doctor" and "Patient" next to combo box | B
Viewer | AA |  | Can sending doctor use viewer and anotize sent image?
COMMENTS 7/12
If error on send ie forgot to specify patient all data shouldn't be removed | B
Drag and drop or upload | AA
Close on image viewer doesn't work | B
View should adapt to aspect ration of image | AA
Leave viewer controls | A | open full image, define width and let image contrain height
Resize icons with | AA | this is a proble because can't do drag and drop with full screen
Title for portal | B | This portal needs to be titled somewhere
Need better solution than toggle screen on top | AA | Maybe Scott has some thoughts
Navigation - statimage should go right to compose message screen | AA
Tooth chart should appear or be accessible on statimage landing screen | AA
Anotization of chart | B
Anotize xray images to be sent | B | Can we use same mechanism to anotize images? Is viewer accessible to sender?
Chart choice - adult, child, perio, soft tissue | A | Adult chart should show with mechanism to switch charts
Dummy up other module landing screens | A